## Sheet1
| Accomplishments | Remaining Tasks | Completed? | Percentage of Each Task | Literature Review Links
2023-04-03 | Literature Review (how to setup IR sensors) | Write Project Description | Yes | 5 | How to Setup an LCD on the Raspberry Pi and Program It With Python - Circuit Basics
2023-04-04 | Wrote out Project Description | Setup IR proximity Sensors | Yes | 5 | Use an RFID reader with the Raspberry Pi. – Howto Raspberry Pi
2023-04-05 | Soldered RFID modules | Setup RFID Module | Yes | 5 | Using Infrared (IR) Sensor with Raspberry Pi - donskytech.com
2023-04-06 | Ordered Raspberry Pi & Sensors | Setup LCD Display | Yes | 5 | https://pycryptodome.readthedocs.io/en/latest/src/cipher/modern.html
2023-04-07 |  | Database for long-term/EV Customers | Yes | 10 | AES Encryption & Decryption In Python: Implementation, Modes & Key Management (onboardbase.com)
2023-04-08 |  | Write Project Interim Review I | Yes | 10 | https://youtu.be/i-h0CtKde6w
2023-04-09 | Literature Review (how to setup LCD Display) | Create Login Window | Yes | 10
2023-04-10 | Raspberry Pi & sensors arrived/Setup proximity sensor module with Raspberry Pi | Write Project Interim Review II | Yes | 10
2023-04-11 | Setup LCD Display with Raspberry Pi/Display if a space is occupied or available | Encrypt Credit Card Number on Payment System | Yes | 5
2023-04-12 | Setup RFID Module | Display Parking space count | Yes | 5
2023-04-13 |  | Integrate payment system, database, sensors, and motors | Yes | 15
2023-04-14 | Tested Individual Components/Modules | Comment Code | Yes | 5
2023-04-15 |  | Submit Final Report | Yes | 10
2023-04-16 |  | Percent Complete (%) | 100
2023-04-17 | Created Signup/Login Window, Setup Database to save login
2023-04-18 | Wrote Project Interim Report I
2023-04-19 | Submitted Project Interim Report I
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24 | Incorporated Hash into login system, linked sign up window
2023-04-25 | Created Payment System Window/GUI
2023-04-26 | Encrypted Payment Method with AES using Cryptodome
2023-04-27 | Programmed Servo motor to trigger with RFID, put into main parking module with sensors
2023-04-28 | Wrote Project Interim II Report
2023-04-29
2023-04-30
2023-05-01 | Worked on integrating LCD to display parking space count from sensors
2023-05-02
2023-05-03
2023-05-04 | Submitted Interim Review II Report
2023-05-05 | Tweaked up module to display parking space count
2023-05-06
2023-05-07 | Worked on final reports
2023-05-08 | Integrated code for all modules/ Added Comments
2023-05-09 | Recorded Demo/ Finished writing final reports
2023-05-10 | Submitted final reports